## Slide 1: Project charter
Date :
Name :
Project Title:
IT Project
Business Case
Delivering IT projects on time and within budget is critical. Delays and requirement changes increase costs and damage client trust. Improving this drives higher revenue and the ability to scale.
Problem Statement (Data-based)
Project is 3 months over schedule with 30% budget overrun and 45% rise in change requests, causing rework and client dissatisfaction.
Goal Statement (SMART)
Reduce project duration from 9 to 6 months and budget variance from 30% to under 10%..
People | 1 | 2 | 3 | 4 | 5 | 6
Name | Jaser | Yazeed | Faisal | Ibrahim | Mohammed | Abdullah
Role | IT Support | Project Manager | Developer | Senior Manager | External Vendor | Business User
Tasks | Maintains system | resources | Build System | Approve | Technical expertise | Use the System
Scope | 1 | 2 | 3 | 4 | 5
In | requirement | Goals | Developers | Changing request | Delivary
Out of |  |  |  |  | 

## Slide 2: Problem statement
Date :
Name :
Problem Description
What is happening? Where is it happening? How big is the problem?
IT project is 3 months over schedule with 30% budget overrun. Requirements changed post-approval, bugs found late in UAT, and teams were not involved early causing rework and misaligned delivery.
DATA
CURRENT PREFORMANCE
Requirements changed post-approval, bugs found late in UAT
IMPACT
Financial
30% budget overrun
TARGET PREFORMANCE
Promoting communication
Operational
3-month delay

## Slide 3: SIPOC
Suppliers | Input | Process | Output | Customer
Customer | Requirements | 1 | Clear Requirements | Customer
Developers | Apply Requirements | 2 | Built System | Customer
Project Manager | Project Follow-up | 3 | Project Stage Results | Developer
External Vendor | Data Entry | 4 | Delivered to Beneficiary | Beneficiary Company
Senior Manager | Project Details | 5 | Project Approval | Project Manager
IT Support | Support Ticket | 6 | Resolved Ticket | Customer

## Slide 4: VOC
SOURCE | RAW VOC | WHY ?
Direct | The project is taking too long | Requirements change
Direct | Requirements keep changing | Unclear goal
Direct | The system has too many bugs | No testing done
Direct | No one explained how to use the system | Poor training
Direct | We were not involved early | Due to requirements change
Direct | The system doesn't match our needs | Misunderstanding
Direct | Issues are not resolved quickly | Poor communication
Direct | The system is slow | High user load
Direct | The final result is disappointing | Misunderstanding

## Slide 5: VOC
SOURCE | RAW VOC | WHY ?
Indirect | Submit repeated change requests after requirements sign-off (+45%) Delay approvals due to unclear requirements | Requirements change
Indirect | Report issues late during UAT (late defect discovery) | Delayed issue resolution
Indirect | Use workarounds instead of system features | Using different methods
Indirect | Log multiple support tickets for the same issue | System bugs
Indirect | Avoid using new system modules (low adoption) | No user manual
Indirect | Escalate issues frequently to management | Lack of technical support
Indirect | Re-open previously “closed” issues | Unresolved issues
Indirect | Spend extra time completing tasks (low efficiency) | Process redesign
Indirect | Continue using legacy systems in parallel | Dependency on old system

## Slide 6: VOC TO CTQ
VOC | NEED | CTQ | METRIC | TARGET

## Slide 7: VOC TO CTQ
VOC | NEED | CTQ | METRIC | TARGET

## Slide 8: STAKEHOLDER ANALYSIS
STAKEHOLDER | TYPE ( INTERNAL/EXTERNAL) | ROLE | INFLUENCE AREA
IDENTIFICATION

## Slide 9: STAKEHOLDER ANALYSIS
STAKEHOLDER | POWER ( H/M/L ) | INTEREST ( H/M/L ) | IMPACT ( H/M/L ) | ATTITUDE ( SUPPORT /NEUTRAL / RESIST )
POWER / INTEREST / IMPACT

## Slide 10: STAKEHOLDER ANALYSIS
STAKEHOLDER | WHAT THEY CARE ABOUT = CTQ | CONFLICT WITH OTHERS ?
VS CTQ

## Slide 11: STAKEHOLDER ANALYSIS
STAKEHOLDER | STRATEGY | FREQUENCY | COMMUNICATION | OWNER
ENGAGEMENT STRATEGY

## Slide 12: STAKEHOLDER ANALYSIS
STAKEHOLDER | FORMAL POWER | INFORMAL INFLUENCE | NETWORK STRENGTH
INFLUENCE MAP

## Slide 13: STAKEHOLDER ANALYSIS
STAKEHOLDER | STRATEGY | FREQUENCY | COMMUNICATION | OWNER
ENGAGEMENT STRATEGY

## Slide 14: STAKEHOLDER ANALYSIS
STAKEHOLDER | RISK TO PROJECT | RISK LEVEL | REASON | MITIGATION STRATEGY
RISK

## Slide 15: STAKEHOLDER ANALYSIS
WHO MATTERS THE MOST | WHO IS RISKY | HOW YOU WILL MANAGE THEM
WHO WILL RESIST SILENTLY | WHO MUST YOU WIN FIRST | WHERE CONFLICT EXISTS
WHO LOSES FROM THIS CHANGE | WHO BENEFITS THE MOST | WHO CAN KILL YOUR PROJECT TOMORROW
THE IDEAL ANALYSIS ANSWERS THESE QUESTIONS